## requirements
Requirement ID | Description | Story Points | Priority | Sprint No. | Sprint | Focus | Requirement IDs
1 | Set up Supabase (PostgreSQL + Auth) for relational data and schedule storage | 5 | 1 | 1 | Sprint 1 | Backend foundation with Supabase integration | 1, 2, 3, 4, 5
2 | Design and implement Express.js backend structure with RESTful routes | 5 | 2 | 1 | Sprint 2 | Schedule management and logic handling | 6, 7, 8, 9
3 | Integrate Supabase Auth (email/password, session management, role claims) | 3 | 3 | 1 | Sprint 3 | Frontend dashboard and schedule visualization | 10, 11, 12, 13, 14
4 | Create API endpoint to fetch course catalog data from Supabase | 2 | 4 | 1 | Final Sprint | Error handling, deployment, and documentation | 15, 16, 17, 18
5 | Design Supabase tables (using JSONB) for flexible schedule storage | 3 | 5 | 1
6 | Implement function to add class to schedule with validation (time conflict, credit limit) | 5 | 6 | 2
7 | Implement function to remove or replace class in schedule | 3 | 7 | 2
8 | Add ability to reset schedule and reload from saved version | 2 | 8 | 2
9 | Implement constraint handling (credit limit, time preferences, prerequisites) | 5 | 9 | 2
10 | Create frontend using Next.js with basic layout and routing for dashboard | 5 | 10 | 3
11 | Develop user dashboard UI with schedule calendar view | 8 | 11 | 3
12 | Enable dynamic course search via department/code filters | 3 | 12 | 3
13 | Implement schedule visualization (calendar-style view of enrolled classes) | 8 | 13 | 3
14 | Add class prerequisite/corequisite validation using catalog table | 3 | 14 | 3
15 | Integrate real-time error handling and loading states in frontend | 3 | 15 | 4
16 | Develop deployment setup with Docker for backend and frontend | 8 | 16 | 4
17 | Create user documentation and onboarding guide for bldr system | 2 | 17 | 4
18 | Prepare final project demo and sprint summary documentation | 3 | 18 | 4