## requirements
Requirement ID | Description | Story Points | Priority | Sprint No.
1 | Set up Supabase (PostgreSQL + Auth) for relational data and schedule storage | 5 | 1 | 1
2 | Design and implement Next API + Supabase backend structure with RESTful routes | 5 | 2 | 2
3 | Integrate Supabase Auth (email/password, session management, role claims) | 3 | 3 | 1
4 | Create API endpoint to fetch course catalog data from Supabase | 2 | 4 | 1
5 | Design Supabase tables (using JSONB) for flexible schedule storage | 3 | 5 | 1
6 | Implement function to add class to schedule with validation (time conflict, credit limit) | 5 | 6 | 2
7 | Implement function to remove or replace class in schedule | 3 | 7 | 2
8 | Add ability to reset schedule and reload from saved version | 2 | 8 | 2
9.1 | Implement credit-limit enforcement when adding classes | 3 | 9 | 2
9.2 | Implement day/time-preference enforcement (no Friday, earliest/latest time, etc.) | 3 | 10 | 2
10 | Create frontend using Next.js with basic layout and routing for dashboard | 5 | 11 | 3
11 | Develop user dashboard UI with schedule calendar view | 8 | 12 | 3
12 | Enable dynamic course search via department/code filters | 3 | 13 | 3
13 | Implement schedule visualization (calendar-style view of enrolled classes) | 8 | 14 | 3
14 | Add class prerequisite/corequisite validation using catalog table | 3 | 16 | 3
15 | Integrate real-time error handling and loading states in frontend | 3 | 15 | 4
16.1 | Containerize backend with Docker (Dockerfile, health-check, env vars) | 5 | 17 | 4
16.2 | Containerize frontend with Docker and configure CI build script | 5 | 18 | 4
17 | Create user documentation and onboarding guide for bldr system | 2 | 19 | 4
18 | Prepare final project demo and sprint summary documentation | 3 | 20 | 4